## GanttChart
Wikinews
Remi – Kafil – Salima – Max
Numéro	Tâche	Début	Fin	Durée

1	Stocker les données	3/01/15	3/08/15	7
1.1	Récupérer des pages HTML avec HTTRACK	3/01/15	3/02/15	1
1.2	Extraire les métadonnées et contenu texte	3/02/15	3/04/15	2
1.3	Indexer le contenu texte	3/04/15	3/06/15	2
1.4	Stocker les données dans MongoDB	3/06/15	3/08/15	2
2	Gérer les requêtes	3/08/15	3/14/15	6
2.1	Indexer les requêtes	3/08/15	3/09/15	1
2.2	Calcul des RSVs	3/09/15	3/11/15	2
2.3	Tri des résultats	3/11/15	3/13/15	2
2.4	Evaluation de la pertinence des résultats	3/13/15	3/14/15	1
3	Créer une interface graphique	3/14/15	3/26/15	12
3.1	Sub Task	3/14/15	3/17/15	3
3.2	Sub Task	3/17/15	3/20/15	3
3.3	Sub Task	3/20/15	3/23/15	3
3.4	Sub Task	3/23/15	3/26/15	3

HELP / - Modify the GREEN cells and the WBS, Tasks, and Task Lead columns. The rest of the columns are formulas. / - The number of weeks shown in the gantt chart is limited by the maximum number of columns available. / - The Start Date that you choose determines the first week in the gantt chart, starting on a Monday. / - Change the first day of the week via cell K8 / - Use the slider to adjust the range of dates shown in the gantt chart. / - Only 34 weeks can be shown/printed at one time, because each week uses up 7 columns. / Q: How do I make Task 2 start the day after the end of Task 1? / Use the following formula for the start date of Task 2: / =EndDate+1 / where EndDate is the reference to the cell containing the end date of task 1 / Q: How do I add/insert tasks and subtasks? / Copy the entire ROW (or a group of rows) for the type of task(s) you want to add and then right-click on the row where you want to insert the new tasks, then select Insert Copied Cells. / Important Note: When inserting a new subtask after the last subtask or before the first subtask, you will need to update the formulas for calculating the Level 1 %Complete and Duration (see below) to include the new subtask, because the ranges won't automatically expand to include the additional row. / Q: How do I calculate the %Complete for a Level 1 task based upon the %Complete of all of the associated subtasks? / Example: If Task 1 is on row 11 and the subtasks are on rows 12-15, use the following formula: / =SUMPRODUCT(F12:F15;G12:G15)/SUM(F12:F15) / Q: How do I calculate the Duration for a Level 1 task based upon the largest end date of a sub task? / Example: If the Level 1 task is on row 11 and the sub tasks are on rows 12-15, use the following formula / =MAX(E12:E15)-D11 / Q: How can I include holidays in the calculation of the Working Days? / You can add a list of holidays to exclude in the NETWORKDAYS function. See the help on that function. / Q: How do I change the print settings? / Select the entire range of cells that you want to print and then define a Print Range in the Format menu. Then go to Format > Page and select the Sheet tab. Adjust the Scaling mode as desired.